## Budget
Job budget tracker
Budgeted against booked, per phase and task. Fill the shaded cells.
Client | Northgate Rail (example) |  |  | Quoted budget (hours) |  | 200
Job | Signalling hazard analysis (example) |  |  | Quoted budget (value) |  | 900000
Currency | INR
Phase | Task | Budget hours | Budget value | Hours booked | Value booked | Remaining hours | Hours used | Remaining value | Value used | Status
Survey | Site walkover | 16 | 72000 | 18.5 | 83250
Survey | Photographs and notes | 8 | 36000 | 6 | 27000
Analysis | Interface hazard log | 60 | 270000 | 41 | 184500
Analysis | Fault tree | 40 | 180000 | 12 | 54000
Reporting | Safety case draft | 50 | 225000
Reporting | Client review |  |  | 2 | 9000
Job totals
|  | Hours | Value
Planned (sum of the lines)
Quoted
Gap (quoted - planned)
Booked against the quote
Made by ReliTime - timesheets, approvals, job costing and GST invoicing for consultancies: https://relitime.com

## How to use
How to use the job budget tracker
1. Fill in the client, the job, and what the job was quoted at, in hours and in money.
2. Add one row per task, with the phase it belongs to. Give it a budget in hours, in money, or both.
3. As work is booked, keep 'Hours booked' and 'Value booked' up to date - weekly is plenty.
4. Remaining and used work themselves out. A row with no budget shows nothing rather than 0%,
because 'nobody estimated this' is not the same as 'nothing has been spent'.
5. Past its budget a row goes negative and above 100%, and is marked Over. Near means 80% or more.
6. 'Planned' is the sum of the lines, shown beside what was quoted. The gap between them is the
thing worth seeing on the day the job is planned. It is withheld until every line has a budget.
7. The example rows are fictional. Replace or clear them.
ReliTime keeps these figures for you from the hours people actually book, per phase and task,
and warns when a job reaches its budget.
Made by ReliTime - timesheets, approvals, job costing and GST invoicing for consultancies: https://relitime.com